## 2026 trajectory
20Oct2026 | Ref | Settlement | Address and planning ref no/ HLA reference | Planning Ref | capacity | 2026-03-01 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | complete | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 5yr NPPF | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 5yr NPPF | comments
|  |  | Table using current Allocations Plan and sites with permission only |  |  | balance left | actual completions (sites over 5 net) |  |  |  | actual completions (sites over 5 net) |  |  |  |  | actual completions (sites over 5 net) | [10 empty] | deliverable | Minimum available 2029-34 (developable) |  |  |  |  | developable
completed
| 2990 | Alvington | Alvington Clanna Lane | 1494/15. 1772/18 RM. | 11 | 0 | [11 empty] | 10 | 1 |  | 11 | [10 empty] | 22 |  | 11 complete 2025
| 2399 | Blakeney | former Goods Station | 367002206813 | 17 | 0 |  |  |  | 17 | [10 empty] | 17 | [10 empty] | 34
| 2861 | Bream | Parkend Rd no 23 net 9 total 13 | 360706206660 | 9 | 0 |  |  |  |  | 9 | [9 empty] | 9 | [10 empty] | 18
| 2871 | Bream | Bream New rd/ High Street | 0636/15, 1736/17. | 9 | 0 | [6 empty] | 9 | [7 empty] | 9 | [10 empty] | 18 |  | 9 dwellings complete 2019
| 2295 | Churcham | Bulley Farm barns | 376193219678 | 6 | 0 |  |  |  |  | 1 | [9 empty] | 1 | [10 empty] | 2
| 2935 | Churcham | Birdwood adj former Chapel | 374171218689 | 7 | 0 |  |  |  |  | 7 | [9 empty] | 7 | [10 empty] | 14
| 1145 | Cinderford | Ruspidge Bracken Close 7 | 365524212637 | 7 | 0
| 2070 | Cinderford | St Whites Sneyd Wood Road | 0558/11 Bloor 2070 | 174 | 50 | 20 | 27 | 13 | [11 empty] | 126 | [12 empty] | Phase 1 complete
| 2217 | Cinderford | St Johns Parish Hall 0344/14 St Johns Mews | 365240212684 | 11 | 0 |  |  | 3 | 3 | 5 | [9 empty] | 11 | [10 empty] | 22
| 2367 | Cinderford | Cinderford Railway Tavern Station St | 0509/16/ful 0469/22. | 12 | 0 | [12 empty] | 12 |  | 12 | [10 empty] | 24 |  | complete 2025
| 2481 | Cinderford | Commercial St no 3 net 7 | 365607213878 | 7 | 0 |  |  |  | 7 | [10 empty] | 7 | [10 empty] | 14
| 2527 | Cinderford | Hollydean net capacity 5 gross 15 | 365406214432 | 5 | 0 |  | 5 | [12 empty] | 5 | [10 empty] | 10
| 2683 | Cinderford | Valley Road 1238/12 Cinders Crescent | 365056213618 | 92 | 0 |  | 16 | 51 | 25 | [10 empty] | 92 | [10 empty] | 184
| 2756 | Cinderford | Cinderford St Whites Rd Peacock Lane Ruspidge | 0678/13. | 16 | 0 |  |  | 5 | 2 | 4 | 5 | 7 | [7 empty] | 16 | [10 empty] | 39 |  | complete
| 2786 | Cinderford | Hanover Court valley Rd | 365139214088 | 20 | 0 |  |  |  | 20 | [10 empty] | 20 | [10 empty] | 40
| 2799 | Cinderford | Ruspidge Villa 6 | 365530212583 | 6 | 0 |  |  |  | 6 | [10 empty] | 6 | [10 empty] | 12
| 2867 | Cinderford | Royal Foresters Court ex PH | 366430214306 | 7 | 0 |  |  |  | 7 | [10 empty] | 7 | [10 empty] | 14
| 3087 | Cinderford | Cinderford 17 Foundry Road |  | 8 | 0 | [5 empty] | 8 | [8 empty] | 8 | [10 empty] | 16 |  | complete
| 3139 | Cinderford | Cinderford St Whites former school | consent 1480/19 | 8 | -1 | [10 empty] | 9 |  |  |  | 9 | [10 empty] | 18 |  | completed April 2023
| 3460 | Cinderford | Cinderford former St Anthony's school | P0971/21 subsequent discons | 8 | 0 | [11 empty] | 8 |  |  | 8 | [10 empty] | 16 |  | complete 2024
| 2442 | Cinderford | Market St 32 7 | 365650213983 | 7 | 0 |  |  | 7 | [11 empty] | 7 | [10 empty] | 14
| 1072 | Coleford | Coalway Rd 27-41 1160/11 Poppy Field | 358470210567 | 41 | 0 |  |  | 2 | 39 | [10 empty] | 41 | [10 empty] | 82
| 1166 | Coleford | Sunnybank Copper Beech Close | 358851210891 | 6 | 0 |  |  |  | 6 | [10 empty] | 6 | [10 empty] | 12
| 1208 | Coleford | Milkwall Station Road Forest Road | 358418209227 | 6 | 0 | [14 empty] | 6 | [10 empty] | 6
| 1814 | Coleford | Coleford former Dukes Travel Lakers Rd Berry Hill | 1002/17 | 7 | 0 | [6 empty] | 7 | [7 empty] | 7 | [10 empty] | 14 |  | complete
| 1966 | Coleford | Woodgate Rd 25 | 359173211836 | 26 | 0 | 2 | 1 | 6 | [11 empty] | 26 | [10 empty] | 35
| 2027 | Coleford | Foxes Lane Broadwell DF6441, 0055/10 | 358884210892 | 7 | 0 |  |  | 7 | [11 empty] | 7 | [10 empty] | 14
| 2225 | Coleford | Pike House B Hill | 357260211966 | 12 | 0 | [14 empty] | 12 | [10 empty] | 12
| 2231 | Coleford | Angel Farm Persimmon HLA2231 Lawdley Rd etc P1229/07allow | 357842210241 | 100 | 0 | 43 | 21 | [12 empty] | 100 | [10 empty] | 164
| 2239 | Coleford | Old Brewery DF10473 | 357610210831 | 6 | 0 | [14 empty] | 6 | [10 empty] | 6
| 2241 | Coleford | High Nash 0832/06 Byrons Meadow | 357734209985 | 7 | 0 | [14 empty] | 7 | [10 empty] | 7
| 2314 | Coleford | Kings Meade 1727/07 | 357853210455 | 14 | 0 |  |  |  |  | 14 | [9 empty] | 14 | [10 empty] | 28
| 2580 | Coleford | Tufthorn hla2580 net increase C11 | 358917209066 | 9 | 0 | 4 | 5 | [12 empty] | 9 | [10 empty] | 18
| 2711 | Coleford | Coleford Owen Farm Staunton Rd | 1167/13 | 90 | 0 |  |  | 10 | 56 | 42 | 38 | 10 | [7 empty] | 90 | [10 empty] | 246 |  | final phase completed by June 2018
| 2758 | Coleford | Bank Street 0438/13 Dora Matthews Hse | 358151210721 | 49 | 0 |  |  | 49 | [11 empty] | 49 | [10 empty] | 98
| 2921 | Coleford | High Nash House High Nash | 357693210114 | 7 | 0 |  |  |  |  | 7 | [9 empty] | 7 | [10 empty] | 14
| 2951 | Coleford | Coleford Ross Rd Christchurch Hall | P1263/13 up to 4 2022 | 6 | 0 | [8 empty] | 2 | 4 |  |  |  |  | 6 | [10 empty] | 12 |  | complete
| 3102 | Coleford | Coleford Lawnstone Hse High St | 0067/18 | 10 | 0 | [7 empty] | 10 | [6 empty] | 10 | [10 empty] | 20 |  | completed 2019
| 3161 | Coleford | Coleford Ex Sonoco Tufthorn Avenue | P0912/16/OUT, 2002/18RM. 1282/23 | 65 | 1 | [9 empty] | 48 | 16 |  |  |  | 64 | [10 empty] | 128 |  | complete
| 3179 | Coleford | Coleford Milkwall Club | P0227/18 | 9 | 0 | [8 empty] | 2 | 2 |  |  | 5 |  | 9 | [10 empty] | 18 |  | complete remainder in small site figures
| 3256 | Coleford | Coleford former Kings Head application | 1266/18 | 8 | 0 | [7 empty] | 4 |  |  |  | 4 |  |  | 8 | [10 empty] | 16 |  | complete 04/24
| 3260 | Coleford | Coleford Lower Lane Berry Hill | 1482/14 (appeal) and 1547/19 | 203 | 0 | [9 empty] | 47 | 60 | 68 | 28 |  | 203 | [10 empty] | 406 |  | capacity now 203, complete
| 3470 | Coleford | Coleford Marians Walk Berry Hill | 1583/20 pp 17 | 17 | 0 | [13 empty] | 17 | 17 | [10 empty] | 34 |  | complete
| 2125 | Drybrook | High St DF10391/D | 365111217407 | 26 | 0 | [14 empty] | 26 | [10 empty] | 26
| 2261 | Drybrook | Nelson Arms | 364150217245 | 6 | 0 |  |  |  |  | 6 | [9 empty] | 6 | [10 empty] | 12
| 3147 | Drybrook | Drybrook High St adj RFC | 1729/16. 0457/20 RM | 57 | 0 | [9 empty] | 33 | 24 |  |  |  | 57 | [10 empty] | 114 |  | completed 2022/23
| 2708 | Dymock | Western Way Winding Pool Close | 370542230868 | 20 | 0 |  |  |  | 20 | [10 empty] | 20 | [10 empty] | 40
| 2161 | Hartpury | Over Old Rd School Close | 380219224740 | 13 | 0 | 13 | [13 empty] | 13 | [10 empty] | 26
| 3385 | Hartpury | Hartpury adj Village Hall Over Old Rd. | 2015/20 full appn 3385 variation 11 | 11 | 0 | [12 empty] | 11 |  | 11 | [10 empty] | 22 |  | complete 2025
| 2838 | Huntley | Orchard Way DF3960 The Fairways | 372779219308 | 33 | 0 | [14 empty] | 33 | [10 empty] | 33
| 3248 | Huntley | Huntley Broom Hill Woodend Farm | 1642/17 3248 conversion 8 | 8 | 0 | [12 empty] | 8 |  | 8 | [10 empty] | 16 |  | Conversion of farm buildings some conditions discharged complete
| 3339 | Huntley | Huntley The Poplars Tibberton Lane | 0946/20 outline RM197/23 10 | 11 | 0 | [12 empty] | 11 |  | 11 | [10 empty] | 22 |  | complete
| 2160 | Littledean | off Oak Way Littledean Three Trees Way | 367187213681 | 9 | 0 | [14 empty] | 9 | [10 empty] | 9
| 2611 | Longhope | Longhope Church Road | 1975/11, 0471/17 Sept 2019 1637/19discon. 2611 2uc 23 | 23 | 0 | [11 empty] | 8 | 15 |  | 23 | [10 empty] | 46 |  | complete
| 3551 | Longhope | Longhope Church Road | 1266/21 12 (CLT scheme) | 12 | 0 | [13 empty] | 12 | 12 | [10 empty] | 24 |  | exceptions scheme commencement early 2024
| 2645 | Lydbrook | Orchard Road Joys Green | 360477216406 | 7 | 0 | 7 | [13 empty] | 7 | [10 empty] | 14
| 1421 | Lydney | adj Health Centre Taurus House | 363694203406 | 8 | 0 | [14 empty] | 8 | [10 empty] | 8
| 2069 | Lydney | Highfield Rd 1089/11 (HLA2069) Meadow Rise | 364912203199 | 47 | 0 |  | 13 | 16 | 18 | [10 empty] | 47 | [10 empty] | 94
| 2126 | Lydney | Regent Street ex Job Centre | 363610203143 | 10 | 0 | 10 | [13 empty] | 10 | [10 empty] | 20
| 2395 | Lydney | Tutnalls Klondike Ave DF13997 gross19 | 363884203077 | 13 | 0 | [14 empty] | 13 | [10 empty] | 13
| 2455 | Lydney | Oakdale 1009/09 Overstreet Green | 364684202356 | 200 | 0 | 39 | 98 | 30 | [11 empty] | 200 | [10 empty] | 367
| 2470 | Lydney | Naas Lane net 7 redevelopment Meadow View | 364444203118 | 7 | 0 | [14 empty] | 7 | [10 empty] | 7
| 2471.1 | Lydney | Lydney East Phase B (RHL site) | 0361/15 Redrow 0076/17 | 125 | 0 | [5 empty] | 21 | 38 | 46 | 20 | [5 empty] | 125 | [10 empty] | 250 |  | completed (125) 2020/21
| 2471.2 | Lydney | Lydney east Phase B (Bellway) | 0835/17. | 90 | 0 | [5 empty] | 5 | 49 | 24 | 12 | [5 empty] | 90 | [10 empty] | 180 |  | completed (90) 2020/21
| 2471.3 | Lydney | Lydney B part | 2471.3 2471.3 0258/20 40 | 40 | 0 | [10 empty] | 32 | 8 |  |  | 40 | [10 empty] | 80 |  | all complete part of Lydney B
| 2471.4 | Lydney | Lydney B part | 2471.4 Crest 148 | 148 | 0 | [9 empty] | 40 | 70 | 38 |  |  | 148 | [10 empty] | 296 |  | all complete part of Lydney B
| 2471.5 | Lydney | Lydney B part | 0260/20 D Wilson 64 | 67 | 0 | [9 empty] | 33 | 28 | 6 |  |  | 67 | [10 empty] | 134 |  | all complete part of Lydney B
| 2672 | Lydney | Pylers way 0762/12 net 7 | 363887202698 | 7 | 0 |  |  | 7 | [11 empty] | 7 | [10 empty] | 14
| 2806 | Lydney | Lydney Highfield Rd rear T & T | 1829/13, 0108/17 0370/19 | 177 | 0 | [6 empty] | 20 | 43 | 56 | 43 | 6 | 9 |  |  | 177 | [10 empty] | 354 |  | complete by March 2024 total 177.
| 2839 | Lydney | 5, 7 Orchard Rd 1691/14 | 364190202687 | 4 | 0 |  |  |  |  | 4 | [9 empty] | 4 | [10 empty] | 8
| 2986 | Lydney | Severnleigh Naas Lane | 364240203108 | 8 | 0 | [5 empty] | 9 | [8 empty] | 9 | [10 empty] | 18
| 3118 | Lydney | Cavendish Buildings Lydney | P1027/18/PO3PA | 6 | 0 | [12 empty] | 6 |  | 6 | [10 empty] | 12
| 3130 | Lydney | Lydney 33 High Street | 1095/18. uc 9 | 9 | 0 | [11 empty] | 9 | 0 |  | 9 | [10 empty] | 18 |  | complete
| 3227 | Lydney | School House Naas Lane | P0074/22/FUL | 6 | 0 | [12 empty] | 6 |  | 6 | [10 empty] | 12
| 1283 | Mitcheldean | Mitcheldean Glos Rd | 0086/09 | 51 | 0 |  | 17 | 17 | 9 | 7 | [9 empty] | 51 | [10 empty] | 101 |  | all complete
| 2272 | Mitcheldean | Eastern avenue 1389/09 | 366810218511 | 7 | 0 | [14 empty] | 7 | [10 empty] | 7
| 1406 | Newent | Culver St Whitegates 1597/09 | 372318225292 | 13 | 0 | 13 | [13 empty] | 13 | [10 empty] | 26
| 2206 | Newent | Meek Rd DF13239/A 141 total D Wilson | 372925225376 | 141 | 0 | 4 | [13 empty] | 4 | [10 empty] | 8
| 2430 | Newent | Culver St Redford Place 31 | 372231225696 | 6 | 0 |  |  |  |  | 6 | [9 empty] | 6 | [10 empty] | 12
| 2452 | Newent | Culver St (Craddocks) net 5 | 372108225459 | 5 | 0 | 3 | 2 | [12 empty] | 5 | [10 empty] | 10
| 2468 | Newent | Foley Rd (Linden Homes) 0264/10 Drovers Way | 372461225442 | 98 | 0 | 21 | 50 | 27 | [11 empty] | 98 | [10 empty] | 196
| 2554 | Newent | Newent Court Road | 1854/13 6 | 6 | 0 | [8 empty] | 1 |  | 5 |  |  |  | 6 | [10 empty] | 12 |  | small redevelopment completed
| 2695 | Newent | Foley Road 0974/15 Manor Road | 372410225256 | 120 | 0 |  |  |  |  | 52 | 68 | [8 empty] | 120 | [10 empty] | 240
| 2777 | Newent | Newent Watery Lane | 1513/13, 1915/15 revised scheme 1338/20 40 | 40 | 0 | [12 empty] | 40 |  | 40 | [10 empty] | 80 |  | complete
| 2834 | Newent | Newent ex Nursery Southend Lane Poinsettia Way 0981/19, | 1877/13, 0047/16. 0981/19 s106 2834 | 36 | 0 | [9 empty] | 36 |  |  |  |  | 36 | [10 empty] | 72 |  | complete
| 2885 | Newent | Newent Ross Rd (Bellway) Horsefair Lane Valegro Avenue | 0328/18. RM approved | 85 | 0 | [6 empty] | 5 | 41 | 39 | [5 empty] | 85 | [10 empty] | 170 |  | completed 2020/21
| 2894 | Newent | Southend Lane Southerns Barn 0241/20 | 372344224912 | 6 | 0 | [9 empty] | 6 |  |  |  |  | 6 | [10 empty] | 12
| 2933 | Newent | Cleeve Mill E Care 1034/11 Mill Park | 372886226136 | 17 | 0 | [5 empty] | 17 | [8 empty] | 17 | [10 empty] | 34
| 3041 | Newent | Newent Southerns Barn Southend Lane | 241/20 | 6 | 0 | [9 empty] | 6 |  |  |  |  | 6 | [10 empty] | 12 |  | complete
| 3105 | Newent | Newent Glebe Gospel Chapel Glebe Court | 1746/17 0039/19 | 8 | 0 | [9 empty] | 8 |  |  |  |  | 8 | [10 empty] | 16 |  | complete
| 3218 | Newent | Newent Southend Lane North | 1330/18. 0041/20RM approved 3280uc 230. | 230 | 0 | [9 empty] | 24 | 104 | 94 | 8 |  | 230 | [10 empty] | 460 |  | allocated in AP, completed March 2025
| 3263 | Newent | 8 Broad Street Newent GL18 1AH | P1193/18/FUL | 6 | 0 | [12 empty] | 6 |  | 6 | [10 empty] | 12
| 3400 | Newent | Newent Bradfords Lane | 1990/18 ol RM 1086/21 uc 50 | 50 | 0 | [10 empty] | 10 | 39 | 1 |  | 50 | [10 empty] | 100 |  | completed March 2025
| 2034 | Newnham | Sheens Meadow DF13276 | 369488211732 | 27 | 0 | 1 | 1 | [12 empty] | 1 | [10 empty] | 3
| 3290 | Newnham | Newnham north of Newnham off A 48 | 1733/18FUL uc 80 | 80 | 0 | [9 empty] | 3 | 35 | 42 |  |  | 80 | [10 empty] | 160 |  | AP allocation- site complete 2023/24,
| 2745 | Redmarley | Hyde Pk Corner 1550/12 | 375743231335 | 10 | 0 |  |  | 10 | [11 empty] | 10 | [10 empty] | 20
| 2963 | Redmarley | Redmarley Drury Lane | 1593/14 0058/17/DISCON | 8 | 0 | [7 empty] | 3 | 1 |  |  | 4 |  |  | 8 | [10 empty] | 16 |  | complete
| 3076 | Redmarley | Redmarley Paget nursery | 181/19 ful | 9 | 0 | [8 empty] | 8 |  | 1 |  |  |  | 9 | [10 empty] | 18 |  | complete
| 2745 | Redmarley | Rock Meadow | 375406231386 | 10 | 0 |  |  | 10 | [11 empty] | 10 | [10 empty] | 20
| 3412 | Redmarley | Redmarley Adj RockMeadow (east of) | 0917/21 | 9 | 0 | [12 empty] | 4 | 5 | 9 | [10 empty] | 18 |  | complete
| 2819 | Sedbury | Sedbury/ Tutshill Adj Wyedean School | 1792/13, 1557/15. 110 | 110 | 0 | [8 empty] | 27 | 57 | 26 |  |  |  | 110 | [10 empty] | 220 |  | complete 2022/23
| 3136 | Sedbury | Sedbury/ Tutshill former garage adj Ormerod Rd | 0815/17 | 10 | 0 | [8 empty] | 10 | [5 empty] | 10 | [10 empty] | 20 |  | site complete
| 2526 | Sling | Miners Close Sling redevelopment net increase 4 | 358257207924 | 4 | 0 | 4 | [13 empty] | 4 | [10 empty] | 8
| 2300 | Soudley | former Coach depot, Bevan Rise | 366327210498 | 13 | 0
| 2950 | St Briavels | Smithville Close | 356792204435 | 9 | 0 | [5 empty] | 9 | [8 empty] | 9 | [10 empty] | 18
| 1713 | Staunton Corse | Corse Grange 0114/13 | 379300228687 | 7 | 0 | [5 empty] | 7 | [8 empty] | 7 | [10 empty] | 14
| 2669 | Staunton Corse | Chartist Way 1680/11 Freedom Close | 378740229094 | 15 | 0 |  | 15 | [12 empty] | 15 | [10 empty] | 30
| 3044 | Staunton Corse | Staunton Corse Chartist Way Hetherington Close | RM appn 848/18. remainder comp? 5 | 27 | 0 | [7 empty] | 1 | 21 | 5 |  |  |  |  | 27 | [10 empty] | 54 |  | complete
| 3194 | Staunton Corse | Staunton Corse Gloucester Rd Yew Tree Close | o/l 1232/18. 1229/19 (RM) | 27 | 0 | [9 empty] | 27 |  |  |  |  | 27 | [10 empty] | 54 |  | all complete
| 3515 | Staunton Corse | Staunton Corse Johnstone Close Staunton GL19 3RR* | 0097/22 | 20 | 0 | [13 empty] | 20 | 20 | [10 empty] | 40 |  | complete
| 2770 | Tibberton | Old Forge 0287/13 Bramble Close | 376688221696 | 9 | 0 |  |  |  | 9 | [10 empty] | 9 | [10 empty] | 18
| 1099 | Tutshill Sedbury | Park View Works Sedbury Court DF4961/J | 354740193459 | 14 | 0
| 1282 | Tutshill Sedbury | Bigstone Meadow DF8773 | 354341194587 | 44 | 0
| 2325 | Tutshill Sedbury | Cross Keys Court | 354438194608 | 12 | 0
| 2819 | Tutshill Sedbury | adj Wyedean School Crane Pool Ave 1792/13 | 354989194028 | 110 | 0 | [8 empty] | 27 | 57 | 26 |  |  |  | 110 | [10 empty] | 220
| 2912 | Tutshill | Sedbury Tutshill Gloucester Rd RM approved Ash Cres. Bellway | 1937/17. | 91 | 0 | [6 empty] | 12 | 34 | 35 | 10 |  |  |  |  | 91 | [10 empty] | 182 |  | all complete
| 2946 | Tutshill | Sedbury Tutshill A48 adj Bigstone Gloucester Rd Birch Grove | 1911/15 651/17. 2946 | 45 | 0 | [6 empty] | 13 | 18 | 14 | [5 empty] | 45 | [10 empty] | 90 |  | all complete
| 3136 | Tutshill Sedbury | adj Ormerod Rd The Beeches | 354644193620 | 10 | 0 | [8 empty] | 10 | [5 empty] | 10 | [10 empty] | 20
| 2709 | Whitecroft | Lydney Rd Redrow 0010/13 Kidnalls Drive | 362377206052 | 49 | 0 |  | 9 | 40 | [11 empty] | 49 | [10 empty] | 98
| 2512 | Woolaston | Severn View Rd Bridge View | 359820200081 | 6 | 0
| 2001 | Yorkley | former bakery 0593/05 The Rudge | 363383206843 | 14 | 0
Superceded/lapsed
| 3333 | Sedbury | Sedbury Former Church Grahamstown Rd | 1969/20 pp 30 04 2021 9 | 0 | 0 | [27 empty] | full consent April 2021 but acquired for office use permitted in 2023, 1288/23
| 2071 | Cinderford | Cinderford Station St Cannop Foundry | 30 LAPSED 2015 AP33 | 130 | 130 | [27 empty] | site available- within plan allocation pre app stage former Listers factory and Cannop Foundry PP0539/08/APP
| 1292 | Cinderford | Cinderford Station St former Listers (Rothdean) | 1590/04 P1578/07/APP LAPSED
| ALL | Cinderford | 82 Valley Road Cinderford | P0885/10/FUL LAPSED | 20 | 20 | [27 empty] | site available- within plan allocation no recent application adjoins larger site in different ownership
| 3296 | Cinderford | Cinderford former health centre Edge Hill Close | 1228/20/PIP see 0273/25/FUL | 0 | 0 | [27 empty] | Permission in Principle for 8 units expired 16/09/2023 future unknown see 0273/25/FUL community centre
Allocations Lapses
| 2640 | Drybrook | Drybrook Farm Drybrook Rd | 1753/12 18 - lapsed | 18 | 18 | [21 empty] | 17 |  |  |  | 17 | 17 | AP allocation has had outline PP now lapsed
| 2878 | Mitcheldean | Mitcheldean former George Hotel | 1849/14/OUT 1106/18 RM pp. expired 2/21 (28) | 18 | 18 | [26 empty] | 0 | AP allocation previous outline permission now lapsed P2066/21/OUT refused
| 2973 | Bream | Bream New Rd/ High St (RFC) site | 1082/14. 1217/19 full 0546/22 revision wd P1978/21/FUL var P1340/21 part of site | 8 | 8 | [27 empty] | AP full pp for 8 (Oct 2020, exp Oct 2023) P1978/21/FUL
| ALL 2843 | Cinderford | Cinderford Northern Quarter, | 0663/14 '195' | 0 | 0 | [26 empty] | 0 | outline pp hybrid which has been part implemented site (FoDDC owned) under review; sold for another use, not counted in housing land supply inside dsb but not allocated in draft LP P0679/21/App withdrawn
Allocations
| APA | Cinderford | Cinderford Football Club Causeway Rd. | AP34 | 80 | 80 | [19 empty] | 50 | 50 | [5 empty] | 0 | Allocated site no permissions or application- P1561/25/FUL resurfacing of turf
| APA | Coleford | Coleford Kings Meade addition | Allocation for 48 | 48 | 48 | [26 empty] | 0 | allocated site remains at early pre application stage
| ALL | Drybrook | Drybrook High Street | Allocation for 50 | 50 | 50 | [18 empty] | 20 | 30 | 50 | [5 empty] | 0 | allocation in AP revised scheme at pre app stage part of revised LP allocation
| ALL | Mitcheldean | Mitcheldean Bradley Court Rd (Vantage Point) | AP84- 40 | 40 | 0 | [26 empty] | 0 | proposed AP allocation not counted in five year supply- no progress
| ALL | Newent | Newent Ross Rd mixed development site. | (0855/19 o/l refused) 30 AP79 | 30 | 0 | [26 empty] | 0 | mixed allocation in AP previous refusal for part development
| ALL | Newent | Newent Cleeve Mill Lane Gloucester Rd | AP76 (45) | 45 | 0 | [18 empty] | 25 | 20 | 45 | [5 empty] | 0 | AP allocated site no application
| ALL | Newnham | Newnham former Victoria Hotel High St | AP99 - 20 | 20 | 20 | [18 empty] | 20 |  | 20 | [5 empty] | 0 | AP allocation some remedial work completed no application
| ALL 2035 | Sling | Sling Adj Miners Arms | 0706/05 refused 1727/08 refused AP105 - 20 | 20 | 20 | [19 empty] | 20 | 20 | [5 empty] | 0 | preapp stage 12/20 no further information
| ALL | Whitecroft | Whitecroft Scovill Lydney Rd Whitecroft. | 0919/19 PDE resolved to grant o/l for 66 | 66 | 66 | [18 empty] | 36 | 30 | 66 | [5 empty] | 0 | outline application delegated approval June 23 awaiting S106
Planning Permissions
| 2002 | Bream | Bream Ryelands Rd (Woodside) | 0422/18/FUL. 0546/13, | 9 | 9 | [18 empty] | 9 |  | 9 | [6 empty] | allocated site has technical commencement full permission for 9 DISCON 13/21- part of an allocation for 15
| 2070.R | Cinderford | Cinderford St Whites Farm Sneyd Wood Rd | 0558/11 | 50 | 50 | [18 empty] | 30 | 20 | 50 | [6 empty] | developable- part covered by unimplemented (valid) consent at pre application stage
| 3456 | Cinderford | Cinderford Valley Road former Engelhards | P1175/18, P0577/20/OUT AP37, P0685/25/APP | 49 | 49 | [15 empty] | 3 | 22 | 24 |  |  | 49 | [6 empty] | P0685/25APP consent Dec 25 for O/L pp 29 09 2022 (49 units and employment space)
| 3399 | Cinderford | Cinderford St Whites former school | 0827/20, 2073/21 new build site 7 | 7 | 3 | [13 empty] | 4 | 4 | 3 |  |  |  |  | 3 | [6 empty] | 7 new build units permitted approval materials etc 2022. Site works underway part complete
| 3542 | Cinderford | Cinderford Sneyd Wood Rd North | 1883/21/FUL 11 | 11 | 11 | [17 empty] | 11 |  |  | 11 | [6 empty] | AP allocation full application approved with S106 agreement Nov 2023
| 2644 | Coleford | Coleford Newland St former WCs | 0285/16. 8, follow P0123/25/FUL reduced in size now 2 | 2 | 2 | [20 empty] | 0 | [6 empty] | no change for many years some foundation work completed 2025 app for 2 dwellings originally 9
| 3600 | Coleford | Coleford Milkwall Ellwood Rd | 2100/21/FUL 47 AP65 | 47 | 47 | [15 empty] | 30 | 17 |  |  |  | 47 | [6 empty] | scheme for 47 (April 2024) previously allocated underconstruction
| 3527 | Coleford | Coleford North Road Worcester Walk Broadwell | 0635/19/Out -35, AP65 70 | 35 | 35 | [17 empty] | 5 | 10 | 20 | 35 | [6 empty] | allocated site part with permission in outline (09/23)
| 3668 | Coleford | Coleford Poolway Farm Gloucester Rd | 1105/22 90 follow 1594/23/FUL | 140 | 140 | [18 empty] | 35 | 35 | 70 | 35 | 35 |  |  |  | 70 | allocated site at full application 1594/23 consent march 26 for 140 dwellings by housebuilder
| 3588 | Hartpury | Hartpury Over Old Road | 0293/22 (26) | 26 | 26 | [15 empty] | 15 | 11 |  |  |  | 26 | [6 empty] | commenced on site
| 2884 | Littledean | Littledean Beech Way | 0899/14 0992/16 app. 2068/20var | 17 | 17 | [17 empty] | 10 | 7 |  | 17 | [6 empty] | allocation with permission appn to vary conditions approved Oct 2022 technical start
| 1010 | Lydbrook | Lydbrook former Rothdean tinplate wks | 1303/13 1165/17 RM (26) | 26 | 26 | [18 empty] | 13 | 13 | 26 | [6 empty] | AP allocation and RM now approved 16/01/2024
| 3550 | Lydney | Lydney East "Liddington" land adj Naas lane & bypass. | 1186/22/ful 70 | 70 | 49 | [12 empty] | 8 | 13 | 21 | 20 | 20 | 9 |  |  | 49 | [6 empty] | linked to adjoining site on this site (70) 10/23 under construction
| 2391 | Lydney | Lydney East (east of Oakdale) | 1881/15 1399/18 347 | 347 | 28 | [7 empty] | 30 | 50 | 25 | 62 | 35 | 69 | 48 | 319 | 20 | 8 |  |  |  | 28 | [6 empty] | permission for 347 dwellings about 330 currently complete,
| 2471.6 | Lydney | Lydney East Phase A (RHL site) | 0412/13, 0745/18 320 876/23 app for 200 | 200 | 153 | [13 empty] | 47 | 47 | 45 | 45 | 25 | 20 | 18 | 153 | [6 empty] | part of allocated site (Lydney A) this part has detailed consent or 200 with developer on site (Bellway)
| ALL R | Lydney | Lydney East Phase A remainder 2471R 120 | 0745/18 o/l 120 units? West of site | 120 | 120 | [21 empty] | 40 | 40 | 40 |  |  | 120 | remainder of Lydney A land and small area N of Naas Lane. Has outline consent.
| 2471.R | Lydney | Lydney east Phase B remainder. 2471R 120 |  | 120 | 120 | [21 empty] | 40 | 40 | 40 |  |  | 120 | remainder of Lydney B with outline consent capacity 150 or 160 approx at pre application stage (750)
| 3057 | Lydney | Lydney Augustus Way Allaston | 1284/13, 1591/18APP 200 | 200 | 200 | [16 empty] | 18 | 30 | 30 | 30 | 108 | 30 | 30 | 17 | 15 |  | 92 | o/l for 200 phase 1 RM appn approved (18) commencement before Oct 2022 (earthworks)
| 3211 | Lydney | Lydney Holms Farm , | 1889/15 29 702/24/APP | 29 | 29 | [18 empty] | 14 | 15 | 29 | [6 empty] | allocation 2005 LP and AP, permission for one conversion and outline for remainder (29) rm submitted P0702/24/APP PCO
| 3655 | Lydney | Land North East of Grove Lane Lydney | 0449/25/OUT & 0885/26/OUT | 80 | 80 | [18 empty] | 5 | 20 | 25 | 20 | 20 | 15 |  |  | 55 | Allowed at appeal P0885/26/OUT PCO Aug26
| 3664 | Mitcheldean | Mitcheldean Former coach depot St Michaels Close | 12 1617/23 9 | 9 | 9 | [18 empty] | 9 |  | 9 | [6 empty] | AP allocation 1617/23 for 9 permission Oct25
| 3629 | Newent | Land At Southend Lane Newent GL18 1JD* | P1711/22/FUL march 25 | 9 | 9 | [18 empty] | 9 |  | 9 | [6 empty] | permission 28/03/2025
| 3620 | Newent | Land At Gloucester Street Newent* | P0584/23/OUT Allowed at appeal Jan 2025 | 375 | 375 | [17 empty] | 40 | 80 | 80 | 200 | 80 | 60 | 20 | 15 |  | 175 | P0993/25/PLANOB consent oct26
| 3380 | Sling | Sling former builders yard | 0452/21 P0448/24/FUL (9) | 9 | 9 | [18 empty] | 9 |  | 9 | [6 empty] | permitted (o/l) 10/1previous outline consent still valid and now revised full application consent
| 3534 | Staunton Corse | Staunton Corse former garden Centre | 0731/22 (16) 1475/23/NONMAT | 16 | 6 | [13 empty] | 10 | 10 | 6 |  |  |  |  | 6 | [6 empty] | full application permitted October 6 2022 DISCON approved commenced
| 3630 | Staunton Corse | Staunton Corse The Swan Ledbury Road* | 0015/24/OUT ALLOW (17) | 17 | 17 | [18 empty] | 9 | 8 | 17 | [6 empty] | Allowed at appeal Feb25
| 3642 | Staunton Corse | Land At Gloucester Road Corse | P0517/23/OUT ALLOW(50) P0685/26/APP consent oct26 | 50 | 50 | [18 empty] | 20 | 20 | 40 | 10 |  |  |  |  | 10 | Allowed at appeal RM approved Oct26
| 3599 | Woolaston/ Netherend | Woolaston/ Netherend Ash Way | 1715/22 OUT application 12 561/26 PCO | 11 | 11 | [16 empty] | 11 |  |  |  | 11 | [6 empty] | allocated site for about 12, current outline appn for 11 P1715/22/OUT ( P0277/22/FUL refused and dismissed at appeal)
| 3357 | Woolaston/ Netherend | Woolaston/ Netherend Farm | 1995/18out 1768/22RM pending 36 | 36 | 24 | [13 empty] | 12 | 12 | 12 | 12 |  |  |  | 24 | [6 empty] | outline permission June 2021 RM approved 25 07 23 commenced and under construction
|  |  | Total in column above |  | 2117 | 1704 |  |  |  |  | 164 | 187 | 170 | 254 | 237 | 438 | 487 | 382 | 239 | 188 |  | 154 | 164 | 154 | 309 | 279 | 1060 | 255 | 225 | 132 | 30 | 0 | 642
|  |  | total all large sites if different to above | [7 empty] | 165 | 187 | 192 | 263 | 298 | 452 | 487 | 307
|  |  | Small sites estimate/ counted | [7 empty] | 82 | 69 | 78 | 73 | 60 | 41 | 30 | 49 | 88 | 85 |  | 60 | 60 | 60 | 60 | 60 | 300 | 60 | 60 | 60 | 60 | 60 | 300
large windfall estimate if applicable
|  |  | total annual net completions or potential | [7 empty] | 247 | 256 | 270 | 336 | 358 | 493 | 517 | 431 | 327 | 303 |  | 214 | 224 | 214 | 369 | 339 | 1360 | 315 | 285 | 192 | 90 | 60 | 942
|  |  | completions on large sites not named above included in annual total | [7 empty] | 112 | 110 | 22
|  |  | from NPPF supply only, calculation for trajectory from this spreadsheet |  |  |  | net recorded completions
|  |  | NPPF compliant |  |  |  | Total delivery
|  |  | Annual requirement |  |  | 598 | plan year | year | tot comp | small site
|  |  | five year net requirement |  |  | 2990 | 1 | 2005/06 | 233 | 116
|  |  | backlog (difference between annual requirement *17 and completions) |  |  | na | 2 | 2006/07 | 205 | 114
|  |  | sub total |  |  | 2990 | 3 | 2007/08 | 405 | 167
|  |  | sub total plus 5%= five year requirement |  |  | 3140 | 4 | 2008/09 | 310 | 114
|  |  | minimum dwellings available |  |  | 1360 | 5 | 2010/11 | 228 | 43
|  |  | years' supply for plan |  |  | 2.27 | 6 | 2011/12 | 265 | 82
|  |  | maximum available |  |  |  | 7 | 2012/13 | 230 | 86
|  |  | years' supply for plan |  |  |  | 8 | 2013/14 | 343 | 75
[7 empty] | 9 | 2014/15 | 372 | 86
[7 empty] | 10 | 2015/16 | 303 | 69
[7 empty] | 11 | 2016/17 | 247 | 82
[7 empty] | 12 | 2017/18 | 256 | 74
[7 empty] | 13 | 2018/19 | 270 | 99
[7 empty] | 14 | 2019/20 | 336 | 73
[7 empty] | 15 | 2020/21 | 358 | 60
[7 empty] | 16 | 2021/22 | 493 | 41
[7 empty] | 17 | 2022/23 | 517 | 30
[7 empty] | 18 | 2023/24 | 431 | 49
[7 empty] | 19 | 2024/25 | 327 | 88
[7 empty] | 20 | 2025/26 | 303 | 85
[7 empty] | Total delivery |  | 6432 | 1632
[7 empty] | average |  | 322 | 82