## Sheet1
2021/ 2022 Housing trajectory data Forest of Dean DC July 2021
|  |  | completions (sites over 5 net) |  |  |  |  | Minimum deliverable |  |  |  |  | Maximum deliverable |  |  |  | Minimum available 2026-31 (developable) |  |  |  |  | Maximum available 2026-31 (developable) |  |  |  |  | min |  |  | max |  |  |  | gridref
Address and planning ref no/ HLA reference | capacity | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 5yr | 6-10yr | 10 yr | 5yr | 6-10 yr | 10yr | comments
Alvington Clanna Lane 1494/15. 1772/18 RM. 2990 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 11 | 11 | 0 | 11 | RM approved April 2019 some subsequent approvals | 360261201009
Bream Ryelands Rd (Woodside) 0546/13, P0422/18/FUL. 2002 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 9 | 0 | 9 | allocated site revised full permission July 2018 following earlier consent DISCON 13/21 | 360675205622
Bream additional land at Ryelands Rd/ Whittington Way | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | no current approval or application: land owned by FoDDC | 360716205563
Bream New Rd/ High St (RFC) site 1082/14. 1217/19 full 2973 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 8 | allocated first in AP. Now subject of new full pp for 8 (Oct 2020) site total 8 site being marketed | 360217205742
Bream New rd/ High Street 0636/15, 1736/17. 2871 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | allocated in AP 9 dwellings now complete | 0
Cinderford 52 Ruspidge Rd 2461/11 1720/16. 2741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no progress previous do not count- potential windfall | 0
Cinderford 97 St Whites Rd Cinderford Bridge 0125/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | not counted no recent progress site in use as garage | 0
Cinderford Adj Bristol House 73 Church Rd 1286/13 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no progress site not counted | 0
Cinderford Football Club Causeway Rd. | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 40 | 40 | 80 | No recent progress, allocated site no permissions or application subject to pre application discussions | 366135214369
Cinderford NQ AAP Newtown Rd site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | sold for another use, remains allocated in AAP but not counted in housing land supply | 0
Cinderford Northern Quarter, AAP 0663/14 2843 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 35 | 40 | 40 | 40 | 35 | 0 | 0 | 195 | 195 | 40 | 155 | 195 | outline pp FoDDC ownership requires revised pp for which there are current applications to access | 364614215590
Cinderford Railway Tavern Station St 0509/16/ful 1539/19 revision. 2367 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 10 | 0 | 10 | valid permission, further discons 71/18 and 35/18. revision approved Jan 2020, 1539/19 | 365192214030
Cinderford St Whites Farm Sneyd Wood Rd 0558/11 2070 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 60 | 0 | 60 | developable- part covered by unimplemented (valid) consent early pre application stage | 365621212625
Cinderford St Whites Rd Peacock Lane Ruspidge 0678/13. | 16 | 4 | 5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete | 0
Cinderford Station St Cannop Foundry 0539/08 2071 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 0 | 30 | site available- within plan allocation no recent application | 365071213919
Cinderford Station St former Listers (Rothdean) 1590/04 1292 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 25 | 0 | 25 | 25 | 25 | 0 | 0 | 0 | 100 | 100 | 25 | 75 | 100 | site available- within plan allocation no recent application | 365181213946
Cinderford Station St Turley Ct and Wilce land 0885/10 2453 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 20 | site available- within plan allocation no recent application | 365015213857
Cinderford Valley Road former Engelhards 1175/18 0577/20 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 0 | 45 | mixed allocation, GP unit recently completed remainder at outline application stage | 365089214541
Cinderford St Whites former school consent 0827/20 3139 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 7 | 15 | 15 | 0 | 15 | permission for 8 under revised application remainder os site being marketed | 365480212853
Cinderford Sneyd Wood Rd North | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 18 | AP allocation at pre application stage 2021 | 365805213104
Cinderford Ruspidge former baths 0011/18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | application for 22 P0011/18 withdrawn status is windfall do not count | 0
Cinderford 17 Foundry Road | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete | 0
Cinderford former health centre | 8 | [12 empty] | 8 | [15 empty] | 8
Coleford former Dukes Travel Lakers Rd Berry Hill 1002/17 1814 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete | 0
Coleford former Kings Head application 1266/18. 3256 | 8 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 3 | 0 | 3 | 5 completed 2019, 3 os, site for sale 01/21 | 357610210795
Coleford Lawnstone Hse High St 0067/18 3102 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all completed 2019 | 357498210568
Coleford Newland St former WCs 0285/16. 2644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | has permission for new build foundations in place available and developable but no activity | 357442210653
Coleford Owen Farm Staunton Rd 1167/13 | 90 | 42 | 38 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | final phase completed by June 2018 | 357825211318
Coleford Poolway Farm Gloucester Rd | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 140 | 140 | 105 | 35 | 140 | allocated site at pre application stage | 357810211324
Coleford Milkwall Ellwood Rd | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 48 | 0 | 48 | allocated site at pre application stage | 358387209130
Coleford Kings Meade addition | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 18 | 18 | 0 | 12 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 48 | 0 | 48 | allocated site at pre application stage | 357880210422
Coleford North Road Worcester Walk Broadwell 0635/19 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 20 | 15 | 20 | 20 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 70 | 70 | 55 | 15 | 70 | allocated site with current application awaiting further information | 358774211641
Coleford Ex Sonoco Tufthorn Avenue P0912/16/OUT, 2002/18RM. 3161 | 65 | 0 | 0 | 0 | 0 | 0 | 35 | 30 | 0 | 0 | 0 | 35 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 65 | 65 | 0 | 65 | 52 under construction August 2020 total 65 | 358010209841
Coleford Ross Rd Christchurch Hall P1263/13 2951 | 6 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 5 | 0 | 5 | site uc | 358156209202
Coleford Milkwall Club 0227/18 3179 | 7 | 0 | 0 | 0 | 0 | 2 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 5 | 0 | 5 | site uc | 357148213010
Coleford Lower lane Berry Hill 1482/14 (appeal) and 1547/19. 3260 | 180 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 40 | 40 | 40 | 20 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 180 | 180 | 0 | 180 | appeal decision April 2018. subsequent RM and approvals, construction under way 30 approx u/c | 357559212147
Drybrook Farm Drybrook Rd 1753/12 2640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 10 | 17 | AP allocation has had outline PP no progress available but constrained | 364563217459
Drybrook High Street | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 50 | allocation in AP revised scheme at pre app stage but no recent progress | 364787217660
Drybrook High St adj RFC1729/16. 0457/20 application for RM 3147 | 57 | 0 | 0 | 0 | 0 | 0 | 30 | 27 | 0 | 0 | 0 | 30 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 57 | 57 | 0 | 57 | now has full permission works commenced on site | 364947217758
Drybrook Nelson arms 2261 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | completed 2016/17 | 0
Hartpury adj Village Hall Over Old Rd. 2015/20 full appn | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 11 | 11 | 0 | 11 | AP allocation- full application now submitted, | 380160224674
Huntley adj The Poplars Tibberton Lane application 0946/20 outline | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | AP allocation outline consent resolved to permit and awaiting s106 | 372678219653
Littledean Beech Way 0899/14 0992/16 app. 2068/20var 2884 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 10 | 0 | 0 | 7 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 17 | 17 | 0 | 17 | AP allocation with full permission current appn to vary conditions but technical start Nov 2018 | 367111213791
Longhope Church Road 1975/11, 0471/17 Sept 2019 1637/19discon. 2611 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 11 | 0 | 0 | 0 | 12 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 23 | 23 | 0 | 23 | revised full permission for 23 and subsequent discons site works commenced | 368408219640
Longhope The Wend 2RH 1888/14 2868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | full permission for affordable housing now lapsed no subsequent pre app not counted | 0
Lydbrook former Rothdean tinplate wks 1303/13 1165/17 RM 1010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 26 | AP allocation and RM appn but delayed. No further information | 359739216247
Lydney East "Liddington" land adj Naas lane & bypass. | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 40 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 0 | 0 | 80 | 80 | 20 | 60 | 80 | allocated but likely to be later phase of AP47 subject to pre app and LP representations | 364635202566
Lydney East (east of Oakdale) 1881/15 1399/18. 2391 | 347 | 0 | 0 | 0 | 30 | 50 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 27 | 0 | 0 | 0 | 40 | 27 | 0 | 0 | 0 | 200 | 67 | 267 | 200 | 67 | 267 | permission for 347 dwellings about 80 currently complete builder on site, uc | 364475202670
Lydney East Phase A (RHL site) 0412/13, 0745/18 2417 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 200 | 200 | 100 | 200 | 300 | allocated and has received outline consent, revised outline application submitted | 364602203180
Lydney East Phase B (RHL site) 0361/15 Redrow 0076/17. 2471.1 | 125 | 0 | 21 | 38 | 46 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | completed (125) 2020/21 | 364373203624
Lydney east Phase B (Bellway) 0835/17. 2471.2 | 90 | 0 | 5 | 49 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | completed (90) 2020/21 | 364538203760
Lydney east Phase B remainder. 2471 R3 | 283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 0 | 0 | 0 | 50 | 80 | 80 | 0 | 0 | 50 | 80 | 80 | 0 | 210 | 210 | 50 | 210 | 260 | remainder of Lydney B not complete (above) or listed below, capacity 283 approx | 364194203661
Lydney Highfield Rd rear T & T 1829/13, 0108/17 0370/19. 2806 | 177 | 0 | 0 | 20 | 43 | 56 | 40 | 18 | 0 | 0 | 0 | 40 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 58 | 58 | 0 | 58 | under construction mostly complete revised total now 177. | 364520203948
Lydney Holms Farm 1325/06, 1889/15. | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 9 | 0 | 10 | 10 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 29 | 0 | 29 | allocation 2005 LP and AP, permission for conversion and outline for remainder (29) | 362807203235
Lydney Augustus Way Allaston 1284/13, 1591/18APP 3057 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 19 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 21 | 40 | 41 | 0 | 0 | 0 | 19 | 181 | 200 | 119 | 81 | 200 | o/l for 200 phase 1 RM appn approved (19) | 363944204430
Lydney 33 High Street 1095/18. 3130 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 9 | 0 | 9 | full consent being marketed, available | 363008203007
Lydney B part 2471.3 2741.3 0258/20 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 60 | 40 | 0 | 40 | full consent part of Lydney B | 364433203789
Lydney B part 2471.4 Crest | 148 | 0 | 0 | 0 | 0 | 0 | 30 | 40 | 40 | 38 | 0 | 30 | 40 | 40 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 148 | 148 | 0 | 148 | full consent now uc part of Lydney B | 363066202914
Lydney B part 0260/20 | 64 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 64 | 64 | 0 | 64 | full consent now uc part of Lydney B | 364441203444
Mitcheldean Former coach depot St Michaels Close | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | AP allocation no current permission | 366271218620
Mitcheldean former George Hotel 1849/14 1106/18 RM pp. 2878 exp2/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 31 | AP allocation O/L permission- RM application approved february 2019 land for sale | 366430218556
Mitcheldean Glos Rd 0086/09 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all complete | 0
Mitcheldean Bradley Court Rd (Vantage Point) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | proposed AP allocation not counted in five year supply- no progress | 366495218939
Newent Ross Rd mixed development site. 0855/19 o/l | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 0 | 30 | mixed allocation in AP previous refusal for part development | 0
Newent Ross Rd (Bellway) Horsefair Lane RM approved 0328/18. 2885 | 85 | 0 | 0 | 5 | 41 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | completed 2020/21 | 371565226290
Newent ex Nursery Southend Lane 1877/13, 0047/16. 0981/19 s106 2834 | 36 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 36 | 36 | 0 | 36 | AP allocation, reserved matters approved commenced on site | 372261224960
Newent Watery Lane 1513/13, 1915/15 revised scheme 1338/20 2777 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 40 | new full application delegated approval April 2021 1338/20 previous RM for 30 | 371535225449
Newent Southend Lane North 1330/18. 0041/20RM approved 3218 | 230 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 200 | 30 | 230 | 200 | 30 | 230 | allocated in AP, outline permission up to 230, RM approved | 372252225163
Newent Cleeve Mill Lane Gloucester Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 15 | 45 | AP allocated site no application | 372881225996
Newent Court Road 1854/13 | 6 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 5 | 0 | 5 | small redevelopment uc | 0
Newent Glebe Gospel Chapel 1746/17 0039/19. 3105 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 8 | current revision for one unit full permission 8 uc | 371987226067
Newent Bradfords Lane 1990/18 ol permission RM application 1086/21 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 50 | 0 | 50 | outline permission RM submitted | 371462225981
Newnham former Victoria Hotel High St | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 20 | AP allocation some remedial work completed | 368978211593
Newnham north of Newnham off A 48 1733/18FUL uc 3290 | 80 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 30 | 0 | 0 | 20 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 80 | 80 | 0 | 80 | AP allocation site under construction | 369187212160
Redmarley Drury Lane 1593/14 0058/17. 2963 | 11 | 0 | 0 | 0 | 3 | 1 | 4 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 4 | 0 | 4 | under construction, part complete | 375350231502
Redmarley Paget nursery 181/19 ful 3076 | 9 | 0 | 0 | 0 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | one unit remaining , otherwise complete | 375348231069
Sedbury Tutshill A48 adj Bigstone Gloucester Rd 1911/15 651/17. 2946 | 45 | 0 | 0 | 13 | 18 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all complete | 354484194610
Sedbury Tutshill Gloucester Rd RM approved 1937/17. 2912 | 91 | 0 | 0 | 12 | 34 | 35 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 10 | 0 | 10 | allocation 10 under construction remainder complete | 354434194835
Sedbury/ Tutshill Adj Wyedean School 1792/13, 1557/15. 2819 | 110 | 0 | 0 | 0 | 0 | 27 | 40 | 43 | 0 | 0 | 0 | 40 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 83 | 83 | 0 | 83 | under construction 64 os remainder complete | 354341194222
Sedbury/ Tutshill Highcliff Beachley Rd Tutshill 1049/15. 1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | site being developed not this scheme do not count | 0
Sedbury/ Tutshill former garage adj Ormerod Rd 0815/17. 3136 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | site complete | 354606193575
Sling Adj Miners Arms 0706/05 2035 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 20 | 2005 LP and AP allocation at preapp stage 12/20 | 358179207933
Staunton Corse Gloucester Rd o/l 1232/18. 1229/19 (RM) 3194 | 27 | 0 | 0 | 0 | 0 | 0 | 13 | 14 | 0 | 0 | 0 | 13 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 27 | 27 | 0 | 27 | AP allocation uc | 379063228926
Staunton/ Corse, Corse Grange 0114/13. | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete | 0
Staunton Corse Chartist Way RM appn 848/18. 3044 | 27 | 0 | 0 | 0 | 1 | 21 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 5 | 0 | 5 | under construction | 378706229116
Whitecroft Scovill Lydney Rd Whitecroft. 0919/19 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 0 | 30 | outline application received | 362060206112
Woolaston/ Netherend Ash Way | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | no progress | 359525200105
Woolaston/ Netherend Farm 1995/18 out permitted 2230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 36 | resolved to permit outline scheme | 359408200192
total in column above | 4286 | 66 | 77 | 170 | 255 | 298
total all large sites |  | 165 | 187 | 192 | 263 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Small sites estimate/ counted | 1768 | 82 | 69 | 78 | 73 | 60 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 370 | 370 | 740 | 370 | 370 | 740
large windfall | [9 empty] | 16 | 32 |  |  |  | 16 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 48 | 200 | 248 | 48 | 200 | 248
total annual net completions or potential |  | 247 | 256 | 270 | 336 | 358 | 469 | 569 | 358 | 298 | 245 | 492 | 664 | 681 | 648 | 606 | 650 | 563 | 456 | 419 | 290 | 504 | 327 | 269 | 269 | 234 | 1939 | 2378 | 4317 | 3092 | 1603 | 4695
completions on large sites not named above included in annual total |  | 99 | 110 | 22 | 8
Summary |  |  | Affordable housing
Annual requirement | 330 |  | AH delivery
five year net requirement | 1650 |  | Year
backlog (difference between annual requirement *15 and completions) | 704 |  | 2007/08 | 80
sub total | 2354 |  | 2008/09 | 38
sub total plus 5%= five year requirement | 2471.7 |  | 2009/10 | 26
total completed in plan period | 4246 |  | 2010/11 | 103
minimum dwellings available | 1919 |  | 2011/12 | 126
years' supply for plan | 3.88 |  | 2012/13 | 177
maximum available | 3092 |  | 2013/14 | 126
years' supply for plan | 6.2548 |  | 2014/15 | 143
Supply identified in delivery paper | 2242 |  | 2015/16 | 114
year's equivalent from delivery paper | 4.5353 |  | 2016/17 | 40
|  |  | 2017/18 | 100
link to delivery paper |  |  | 2018/19 | 20
|  |  | 2019/20 | 78
|  |  | 2020/21 | 78
Total delivery
| plan year | year | tot comp | small site
| 1 | 2006/07 | 205 | 114
| 2 | 2007/08 | 405 | 167
| 3 | 2008/09 | 310 | 114
| 4 | 2009/10 | 118 | 43
| 5 | 2010/11 | 228 | 43
| 6 | 2011/12 | 265 | 82
| 7 | 2012/13 | 230 | 86
| 8 | 2013/14 | 343 | 75
| 9 | 2014/15 | 372 | 86
| 10 | 2015/16 | 303 | 69 |  |  |  |  | graph:
| 11 | 2016/17 | 247 | 82 |  |  |  |  | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31
| 12 | 2017/18 | 256 | 69 |  |  |  |  | graph: 2016/17: 247; graph: 2017/18: 256; graph: 2018/19: 270; graph: 2019/20: 336; graph: 2020/21: 358
| 13 | 2018/19 | 270 | 78 |  |  |  |  | graph: 2021/22: 469; graph: 2022/23: 569; graph: 2023/24: 358; graph: 2024/25: 298; graph: 2025/26: 245
| 14 | 2019/20 | 336 | 73 |  |  |  |  | graph: 2026/27: 650; graph: 2027/28: 563; graph: 2028/29: 456; graph: 2029/30: 419; graph: 2030/31: 290
| 15 | 2020/21 | 358 | 60 |  |  |  |  | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330
| 16 | 2021/22
| 17 | 2022/23
| 18 | 2023/24
| 19 | 2024/25
| 20 | 2025/26
| Total delivery |  | 4246 | 1241
| average |  | 283.0667 | 82.7333