{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":1,"images":0,"macros":0,"external_links":1,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":165,"n_cols":35,"rows_kept":165,"cut":false,"hidden":false,"merged":[]}
["2021/ 2022 Housing trajectory data Forest of Dean DC  July 2021"]
[]
[null,null,null,"completions  (sites over 5 net)",{"$nulls":4},"Minimum  deliverable",{"$nulls":4},"Maximum deliverable",null,null,null,"Minimum available 2026-31 (developable)",{"$nulls":4},"Maximum available 2026-31 (developable)",{"$nulls":4},"min ",null,null,"max",null,null,null,"gridref"]
["Address and planning ref no/ HLA reference","capacity","2016/17","2017/18","2018/19","2019/20","2020/21","2021/22","2022/23","2023/24","2024/25","2025/26","2021/22","2022/23","2023/24","2024/25","2025/26","2026/27","2027/28","2028/29","2029/30","2030/31","2026/27","2027/28","2028/29","2029/30","2030/31","5yr","6-10yr","10 yr","5yr","6-10 yr","10yr","comments"]
["Alvington Clanna Lane 1494/15. 1772/18 RM. 2990",11,0,0,0,0,0,0,0,11,0,0,0,11,0,0,0,0,0,0,0,0,0,0,0,0,0,11,0,11,11,0,11,"RM approved April 2019 some subsequent approvals","360261201009"]
[]
["Bream Ryelands Rd (Woodside)  0546/13, P0422/18/FUL. 2002",9,0,0,0,0,0,0,9,0,0,0,0,9,0,0,0,0,0,0,0,0,0,0,0,0,0,9,0,9,9,0,9,"allocated site revised full permission July 2018 following earlier consent DISCON 13/21","360675205622"]
["Bream additional land at Ryelands Rd/ Whittington Way",0,0,0,0,0,0,0,0,0,0,0,0,0,0,5,0,0,0,0,0,0,0,0,0,0,0,0,0,0,5,0,5,"no current approval or application: land owned by FoDDC","360716205563"]
["Bream New Rd/ High St (RFC) site 1082/14. 1217/19 full 2973",8,0,0,0,0,0,0,0,0,8,0,0,0,8,0,0,0,0,0,0,0,0,0,0,0,0,8,0,8,8,0,8,"allocated first in AP. Now subject of new full pp for 8 (Oct 2020) site total 8 site being marketed","360217205742"]
["Bream New rd/ High Street 0636/15, 1736/17. 2871",9,0,0,9,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"allocated  in AP  9 dwellings now complete",0]
[]
["Cinderford 52 Ruspidge Rd 2461/11 1720/16. 2741",0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"no progress previous  do not count- potential windfall",0]
["Cinderford 97 St Whites Rd  Cinderford Bridge 0125/08",0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"not counted no recent progress site in use as garage",0]
["Cinderford Adj Bristol House 73 Church Rd 1286/13 2750",0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"no progress site not counted",0]
["Cinderford Football Club Causeway Rd. ",80,0,0,0,0,0,0,0,0,0,0,0,0,0,0,40,40,40,0,0,0,40,0,0,0,0,0,80,80,40,40,80,"No recent progress, allocated site no permissions or application subject to pre application discussions","366135214369"]
["Cinderford NQ AAP Newtown Rd site",0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"sold for another use, remains allocated in AAP but not counted in housing land supply",0]
["Cinderford Northern Quarter, AAP 0663/14 2843",195,0,0,0,0,0,0,0,0,0,0,0,0,0,0,40,40,40,40,40,35,40,40,40,35,0,0,195,195,40,155,195,"outline pp  FoDDC ownership requires revised pp for which there are current applications to access","364614215590"]
["Cinderford Railway Tavern Station St  0509/16/ful 1539/19 revision. 2367",10,0,0,0,0,0,0,10,0,0,0,10,0,0,0,0,0,0,0,0,0,0,0,0,0,0,10,0,10,10,0,10,"valid permission, further discons 71/18 and 35/18. revision approved Jan 2020, 1539/19","365192214030"]
["Cinderford St Whites Farm Sneyd Wood Rd 0558/11 2070",60,0,0,0,0,0,0,0,0,0,0,0,0,30,30,0,0,30,30,0,0,0,0,0,0,0,0,60,60,60,0,60,"developable- part covered by unimplemented (valid) consent early pre application stage","365621212625"]
["Cinderford St Whites Rd Peacock Lane Ruspidge 0678/13.",16,4,5,7,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"complete",0]
["Cinderford Station St Cannop Foundry 0539/08 2071",30,0,0,0,0,0,0,0,0,0,0,0,0,0,15,15,0,0,0,30,0,0,0,0,0,0,0,30,30,30,0,30,"site available- within plan allocation no recent application ","365071213919"]
["Cinderford Station St former Listers (Rothdean) 1590/04 1292",100,0,0,0,0,0,0,0,0,0,0,0,0,0,0,25,25,25,25,25,0,25,25,25,0,0,0,100,100,25,75,100,"site available- within plan allocation no recent application","365181213946"]
["Cinderford Station St Turley Ct and Wilce land 0885/10 2453",20,0,0,0,0,0,0,0,0,0,0,0,0,0,10,10,0,0,20,0,0,0,0,0,0,0,0,20,20,20,0,20,"site available- within plan allocation no recent application","365015213857"]
["Cinderford Valley Road former Engelhards 1175/18 0577/20",45,0,0,0,0,0,0,0,0,0,0,0,0,15,15,15,15,15,15,0,0,0,0,0,0,0,0,45,45,45,0,45,"mixed allocation, GP unit recently completed remainder at outline application stage","365089214541"]
["Cinderford St Whites former school consent 0827/20 3139",15,0,0,0,0,0,0,8,0,0,0,8,0,0,7,0,7,0,0,0,0,0,0,0,0,0,8,7,15,15,0,15,"permission for 8 under revised application remainder os site being marketed","365480212853"]
["Cinderford  Sneyd Wood Rd North",18,0,0,0,0,0,0,0,0,0,0,0,18,0,0,0,18,0,0,0,0,0,0,0,0,0,0,18,18,18,0,18,"AP allocation at pre application stage 2021","365805213104"]
["Cinderford Ruspidge former baths 0011/18",0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"application for 22 P0011/18 withdrawn status is windfall do not count",0]
["Cinderford 17 Foundry Road",8,0,8,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"complete",0]
["Cinderford former health centre",8,{"$nulls":12},8,{"$nulls":15},8]
[]
["Coleford  former Dukes Travel Lakers Rd Berry Hill  1002/17 1814",7,0,0,7,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"complete",0]
["Coleford former Kings Head application 1266/18. 3256",8,0,0,0,5,0,0,0,0,3,0,0,3,0,0,0,0,0,0,0,0,0,0,0,0,0,3,0,3,3,0,3,"5 completed 2019, 3 os,  site for sale 01/21","357610210795"]
["Coleford Lawnstone Hse High St 0067/18 3102",10,0,0,0,10,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"all completed 2019","357498210568"]
["Coleford Newland St former WCs 0285/16. 2644",0,0,0,0,0,0,0,0,0,0,0,0,0,8,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,8,0,8,"has permission for new build foundations in place available and developable but no activity","357442210653"]
["Coleford Owen Farm Staunton Rd 1167/13",90,42,38,10,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"final phase  completed by June 2018","357825211318"]
["Coleford Poolway Farm Gloucester Rd",140,0,0,0,0,0,0,0,0,0,0,0,0,35,35,35,35,35,35,35,0,35,0,0,0,0,0,140,140,105,35,140,"allocated site at pre application stage","357810211324"]
["Coleford Milkwall Ellwood Rd",48,0,0,0,0,0,0,0,0,0,0,0,0,24,24,0,24,24,0,0,0,0,0,0,0,0,0,48,48,48,0,48,"allocated site at pre application stage  ","358387209130"]
["Coleford Kings Meade addition",48,0,0,0,0,0,0,0,0,0,0,0,12,18,18,0,12,18,18,0,0,0,0,0,0,0,0,48,48,48,0,48,"allocated site at pre application stage","357880210422"]
["Coleford North Road Worcester Walk Broadwell 0635/19",70,0,0,0,0,0,0,0,0,0,0,0,0,15,20,20,15,20,20,15,0,15,0,0,0,0,0,70,70,55,15,70,"allocated site with current application awaiting further information ","358774211641"]
["Coleford Ex Sonoco Tufthorn Avenue P0912/16/OUT, 2002/18RM.  3161",65,0,0,0,0,0,35,30,0,0,0,35,30,0,0,0,0,0,0,0,0,0,0,0,0,0,65,0,65,65,0,65,"52 under construction August 2020 total 65","358010209841"]
["Coleford Ross Rd Christchurch Hall P1263/13 2951",6,0,0,0,0,2,4,0,0,0,0,4,0,0,0,0,0,0,0,0,0,0,0,0,0,0,4,0,4,5,0,5,"site uc ","358156209202"]
["Coleford Milkwall Club 0227/18 3179",7,0,0,0,0,2,0,5,0,0,0,5,0,0,0,0,0,0,0,0,0,0,0,0,0,0,5,0,5,5,0,5,"site uc ","357148213010"]
["Coleford Lower lane Berry Hill 1482/14 (appeal) and 1547/19. 3260",180,0,0,0,0,0,20,40,40,40,40,20,40,40,40,40,0,0,0,0,0,0,0,0,0,0,180,0,180,180,0,180,"appeal decision April 2018. subsequent RM and approvals,  construction under way 30 approx u/c","357559212147"]
[]
["Drybrook Farm Drybrook Rd 1753/12 2640",0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,7,0,0,0,0,0,10,0,0,0,0,0,0,0,7,10,17,"AP allocation has had outline PP no progress available but constrained","364563217459"]
["Drybrook High Street",50,0,0,0,0,0,0,0,0,0,0,0,0,0,20,30,20,30,0,0,0,0,0,0,0,0,0,50,50,50,0,50,"allocation in AP revised scheme at pre app stage but no recent progress","364787217660"]
["Drybrook High St  adj RFC1729/16.  0457/20 application for RM 3147",57,0,0,0,0,0,30,27,0,0,0,30,27,0,0,0,0,0,0,0,0,0,0,0,0,0,57,0,57,57,0,57,"now has full permission works commenced on site","364947217758"]
["Drybrook Nelson arms 2261",6,6,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"completed 2016/17",0]
[]
["Hartpury adj Village Hall Over Old Rd.  2015/20 full appn",11,0,0,0,0,0,0,11,0,0,0,0,11,0,0,0,0,0,0,0,0,0,0,0,0,0,11,0,11,11,0,11,"AP allocation- full application now submitted, ","380160224674"]
[]
["Huntley adj The Poplars Tibberton Lane application  0946/20 outline",10,0,0,0,0,0,0,0,0,0,0,0,10,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,10,0,10,"AP allocation outline consent resolved to permit and awaiting s106","372678219653"]
[]
["Littledean Beech Way  0899/14 0992/16 app. 2068/20var 2884",17,0,0,0,0,0,0,0,7,10,0,0,7,10,0,0,0,0,0,0,0,0,0,0,0,0,17,0,17,17,0,17,"AP allocation with full permission current appn to vary conditions but technical start Nov 2018","367111213791"]
[]
["Longhope Church Road 1975/11, 0471/17 Sept 2019 1637/19discon. 2611",23,0,0,0,0,0,0,12,11,0,0,0,12,11,0,0,0,0,0,0,0,0,0,0,0,0,23,0,23,23,0,23,"revised full permission for 23 and subsequent discons site works commenced","368408219640"]
["Longhope The Wend 2RH 1888/14 2868",0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"full permission for affordable housing now lapsed no subsequent pre app not counted",0]
[]
["Lydbrook former Rothdean tinplate wks   1303/13  1165/17 RM 1010",0,0,0,0,0,0,0,0,0,0,0,0,0,0,13,13,0,0,0,0,0,0,0,0,0,0,0,0,0,26,0,26,"AP allocation and RM appn but delayed.  No further information ","359739216247"]
[]
["Lydney East \"Liddington\" land adj Naas lane & bypass.",80,0,0,0,0,0,0,0,0,0,0,0,0,0,0,20,40,40,0,0,0,40,20,0,0,0,0,80,80,20,60,80,"allocated but likely to be later phase of AP47 subject to pre app and LP representations","364635202566"]
["Lydney East (east of Oakdale) 1881/15 1399/18. 2391",347,0,0,0,30,50,40,40,40,40,40,40,40,40,40,40,40,27,0,0,0,40,27,0,0,0,200,67,267,200,67,267,"permission for 347 dwellings about 80 currently complete builder on site, uc","364475202670"]
["Lydney East Phase A (RHL site) 0412/13, 0745/18 2417",200,0,0,0,0,0,0,0,0,0,0,0,0,20,40,40,40,40,40,40,40,40,40,40,40,40,0,200,200,100,200,300,"allocated and has received outline consent, revised outline application submitted","364602203180"]
["Lydney East Phase B (RHL site) 0361/15 Redrow 0076/17. 2471.1",125,0,21,38,46,20,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"completed (125) 2020/21","364373203624"]
["Lydney east Phase B (Bellway) 0835/17. 2471.2",90,0,5,49,24,12,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"completed (90) 2020/21","364538203760"]
["Lydney east Phase B remainder. 2471 R3",283,0,0,0,0,0,0,0,0,0,0,0,0,20,30,0,0,0,50,80,80,0,0,50,80,80,0,210,210,50,210,260,"remainder of Lydney B not complete (above) or listed below, capacity 283 approx","364194203661"]
["Lydney Highfield Rd rear T & T 1829/13,  0108/17 0370/19. 2806",177,0,0,20,43,56,40,18,0,0,0,40,18,0,0,0,0,0,0,0,0,0,0,0,0,0,58,0,58,58,0,58,"under construction mostly complete revised total now 177.","364520203948"]
["Lydney Holms Farm 1325/06, 1889/15.",29,0,0,0,0,0,0,0,0,0,0,0,10,10,9,0,10,10,9,0,0,0,0,0,0,0,0,29,29,29,0,29,"allocation 2005 LP and AP, permission for conversion and outline for remainder (29)","362807203235"]
["Lydney Augustus Way Allaston 1284/13, 1591/18APP 3057",200,0,0,0,0,0,0,0,0,0,19,0,19,20,40,40,40,40,40,40,21,40,41,0,0,0,19,181,200,119,81,200,"o/l for 200  phase 1 RM appn approved  (19)","363944204430"]
["Lydney 33 High Street 1095/18. 3130",9,0,0,0,0,0,0,0,0,9,0,0,9,0,0,0,0,0,0,0,0,0,0,0,0,0,9,0,9,9,0,9,"full consent being marketed, available","363008203007"]
["Lydney B part 2471.3 2741.3 0258/20",60,0,0,0,0,0,0,20,20,20,0,0,20,20,0,0,0,0,0,0,0,0,0,0,0,0,60,0,60,40,0,40,"full consent part of Lydney B","364433203789"]
["Lydney B part 2471.4 Crest",148,0,0,0,0,0,30,40,40,38,0,30,40,40,38,0,0,0,0,0,0,0,0,0,0,0,148,0,148,148,0,148,"full consent now uc part of Lydney B","363066202914"]
["Lydney B part  0260/20",64,0,0,0,0,0,32,32,0,0,0,32,32,0,0,0,0,0,0,0,0,0,0,0,0,0,64,0,64,64,0,64,"full consent now uc part of Lydney B","364441203444"]
[]
["Mitcheldean Former coach depot St Michaels Close ",0,0,0,0,0,0,0,0,0,0,0,0,0,0,12,0,0,0,0,0,0,0,0,0,0,0,0,0,0,12,0,12,"AP allocation no current permission ","366271218620"]
["Mitcheldean former George Hotel 1849/14 1106/18 RM pp. 2878 exp2/21",0,0,0,0,0,0,0,0,0,0,0,0,0,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,31,0,31,"AP allocation O/L permission-  RM application approved february 2019 land for sale","366430218556"]
["Mitcheldean Glos Rd 0086/09",7,7,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"all complete",0]
["Mitcheldean Bradley Court Rd (Vantage Point)",0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,20,20,0,0,0,0,0,0,0,40,40,"proposed AP allocation not counted in five year supply- no progress","366495218939"]
[]
["Newent Ross Rd mixed development site. 0855/19 o/l",30,0,0,0,0,0,0,0,0,0,0,0,0,0,15,15,15,15,0,0,0,0,0,0,0,0,0,30,30,30,0,30,"mixed allocation in AP previous refusal for part development",0]
["Newent Ross Rd (Bellway) Horsefair Lane RM approved 0328/18. 2885",85,0,0,5,41,39,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"completed 2020/21","371565226290"]
["Newent ex Nursery Southend Lane 1877/13, 0047/16. 0981/19 s106 2834",36,0,0,0,0,0,18,18,0,0,0,18,18,0,0,0,0,0,0,0,0,0,0,0,0,0,36,0,36,36,0,36,"AP allocation, reserved matters approved  commenced on site","372261224960"]
["Newent Watery Lane 1513/13, 1915/15 revised scheme 1338/20 2777",40,0,0,0,0,0,0,20,20,0,0,0,20,20,0,0,0,0,0,0,0,0,0,0,0,0,40,0,40,40,0,40,"new full application delegated approval April 2021 1338/20 previous RM for 30","371535225449"]
["Newent Southend Lane North 1330/18. 0041/20RM approved 3218",230,0,0,0,0,0,40,40,40,40,40,40,40,40,40,40,30,0,0,0,0,30,0,0,0,0,200,30,230,200,30,230,"allocated in AP, outline permission up to 230, RM approved ","372252225163"]
["Newent Cleeve Mill Lane Gloucester Rd",0,0,0,0,0,0,0,0,0,0,0,0,0,0,15,15,0,0,0,0,0,15,0,0,0,0,0,0,0,30,15,45,"AP allocated site no application","372881225996"]
["Newent Court Road 1854/13",6,0,0,0,0,1,5,0,0,0,0,5,0,0,0,0,0,0,0,0,0,0,0,0,0,0,5,0,5,5,0,5,"small redevelopment uc",0]
["Newent Glebe Gospel Chapel 1746/17 0039/19. 3105",8,0,0,0,0,0,8,0,0,0,0,8,0,0,0,0,0,0,0,0,0,0,0,0,0,0,8,0,8,8,0,8,"current revision for one unit full permission  8 uc","371987226067"]
["Newent Bradfords Lane 1990/18 ol permission RM application 1086/21",50,0,0,0,0,0,0,25,25,0,0,0,25,25,0,0,0,0,0,0,0,0,0,0,0,0,50,0,50,50,0,50,"outline permission RM submitted","371462225981"]
[]
["Newnham former Victoria Hotel High St",20,0,0,0,0,0,0,0,0,0,0,0,0,20,0,0,20,0,0,0,0,0,0,0,0,0,0,20,20,20,0,20,"AP allocation some remedial work completed","368978211593"]
["Newnham north of Newnham off A 48 1733/18FUL uc 3290",80,0,0,0,0,0,20,30,30,0,0,20,30,30,0,0,0,0,0,0,0,0,0,0,0,0,80,0,80,80,0,80,"AP allocation site under construction ","369187212160"]
[]
["Redmarley Drury Lane 1593/14 0058/17. 2963",11,0,0,0,3,1,4,3,0,0,0,4,0,0,0,0,0,0,0,0,0,0,0,0,0,0,7,0,7,4,0,4,"under construction, part complete","375350231502"]
["Redmarley Paget nursery 181/19 ful 3076",9,0,0,0,0,8,1,0,0,0,0,1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,1,0,1,1,0,1,"one unit remaining , otherwise complete","375348231069"]
[]
["Sedbury Tutshill A48 adj Bigstone Gloucester Rd 1911/15 651/17. 2946",45,0,0,13,18,14,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"all complete","354484194610"]
["Sedbury Tutshill Gloucester Rd RM approved 1937/17. 2912",91,0,0,12,34,35,10,0,0,0,0,10,0,0,0,0,0,0,0,0,0,0,0,0,0,0,10,0,10,10,0,10,"allocation 10 under construction remainder complete","354434194835"]
["Sedbury/ Tutshill Adj Wyedean School 1792/13, 1557/15. 2819",110,0,0,0,0,27,40,43,0,0,0,40,43,0,0,0,0,0,0,0,0,0,0,0,0,0,83,0,83,83,0,83,"under construction 64 os remainder complete","354341194222"]
["Sedbury/ Tutshill Highcliff Beachley Rd Tutshill 1049/15. 1932",0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0," site being developed not this scheme do not count",0]
["Sedbury/ Tutshill former garage adj Ormerod Rd 0815/17. 3136",10,0,0,0,0,10,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"site complete","354606193575"]
[]
["Sling Adj Miners Arms 0706/05 2035",20,0,0,0,0,0,0,0,0,0,0,0,10,10,0,0,20,0,0,0,0,0,0,0,0,0,0,20,20,20,0,20,"2005 LP and AP allocation at preapp stage 12/20","358179207933"]
[]
["Staunton Corse Gloucester Rd o/l   1232/18. 1229/19 (RM) 3194",27,0,0,0,0,0,13,14,0,0,0,13,14,0,0,0,0,0,0,0,0,0,0,0,0,0,27,0,27,27,0,27,"AP allocation uc","379063228926"]
["Staunton/ Corse, Corse Grange 0114/13.",7,7,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,"complete",0]
["Staunton Corse Chartist Way RM appn  848/18. 3044",27,0,0,0,1,21,5,0,0,0,0,5,0,0,0,0,0,0,0,0,0,0,0,0,0,0,5,0,5,5,0,5,"under construction ","378706229116"]
[]
["Whitecroft Scovill Lydney Rd Whitecroft. 0919/19",30,0,0,0,0,0,0,0,0,0,0,0,0,15,15,0,30,0,0,0,0,0,0,0,0,0,0,30,30,30,0,30,"outline application received ","362060206112"]
[]
["Woolaston/ Netherend Ash Way",0,0,0,0,0,0,0,0,0,0,0,0,0,12,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,12,0,12,"no progress","359525200105"]
["Woolaston/ Netherend Farm 1995/18 out  permitted 2230",0,0,0,0,0,0,0,0,0,0,0,0,12,12,12,0,0,0,0,0,0,0,0,0,0,0,0,0,0,36,0,36,"resolved to permit outline scheme","359408200192"]
[]
[]
["total in column above",4286,66,77,170,255,298]
["total all large sites",null,165,187,192,263,298,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
["Small sites estimate/ counted",1768,82,69,78,73,60,74,74,74,74,74,74,74,74,74,74,74,74,74,74,74,74,74,74,74,74,370,370,740,370,370,740]
["large windfall",{"$nulls":9},16,32,null,null,null,16,32,40,40,40,40,40,40,40,40,40,40,48,200,248,48,200,248]
["total annual net completions or potential",null,247,256,270,336,358,469,569,358,298,245,492,664,681,648,606,650,563,456,419,290,504,327,269,269,234,1939,2378,4317,3092,1603,4695]
["completions on large sites not named above included in annual total",null,99,110,22,8]
[]
[]
[]
[]
["Summary",null,null,"Affordable housing"]
["Annual requirement",330,null,"AH delivery"]
["five year net requirement",1650,null,"Year"]
["backlog (difference between annual requirement *15 and completions)",704,null,"2007/08",80]
["sub total",2354,null,"2008/09",38]
["sub total plus 5%= five year requirement",2471.7000000000003,null,"2009/10",26]
["total completed in plan period",4246,null,"2010/11",103]
["minimum dwellings available",1919,null,"2011/12",126]
["years' supply for plan",3.88,null,"2012/13",177]
["maximum available",3092,null,"2013/14",126]
["years' supply for plan",6.2548043856455058,null,"2014/15",143]
["Supply identified in delivery paper",2242,null,"2015/16",114]
["year's equivalent from delivery paper",4.5353400493587408,null,"2016/17",40]
[null,null,null,"2017/18",100]
["link to delivery paper",null,null,"2018/19",20]
[null,null,null,"2019/20",78]
[null,null,null,"2020/21",78]
[]
[null,"Total delivery"]
[null,"plan year","year","tot comp","small site"]
[null,1,"2006/07",205,114]
[null,2,"2007/08",405,167]
[null,3,"2008/09",310,114]
[null,4,"2009/10",118,43]
[null,5,"2010/11",228,43]
[null,6,"2011/12",265,82]
[null,7,"2012/13",230,86]
[null,8,"2013/14",343,75]
[null,9,"2014/15",372,86]
[null,10,"2015/16",303,69,{"$nulls":4},"graph:"]
[null,11,"2016/17",247,82,{"$nulls":4},"2016/17","2017/18","2018/19","2019/20","2020/21","2021/22","2022/23","2023/24","2024/25","2025/26","2026/27","2027/28","2028/29","2029/30","2030/31"]
[null,12,"2017/18",256,69,{"$nulls":4},247,256,270,336,358]
[null,13,"2018/19",270,78,{"$nulls":9},469,569,358,298,245]
[null,14,"2019/20",336,73,{"$nulls":14},650,563,456,419,290]
[null,15,"2020/21",358,60,{"$nulls":4},330,330,330,330,330,330,330,330,330,330,330,330,330,330,330]
[null,16,"2021/22"]
[null,17,"2022/23"]
[null,18,"2023/24"]
[null,19,"2024/25"]
[null,20,"2025/26"]
[null,"Total delivery",null,4246,1241]
[null,"average",null,283.06666666666666,82.733333333333334]